## Project Planner
BUSINESS CELEBRATION PROJECT PLAN
GROUNDBREAKINGS, RIBBON CUTTINGS, GRAND OPENINGS
PERIODS: LIST WEEKS HERE (12 WEEKS ARE RECOMMENDED)
PLAN START=WEEK YOU ARE STARTING YOUR PLAN
ACTUAL START=ACTUAL WEEK YOU STARTED WORKING ON THAT ITEM
PLAN DURATION=HOW MANY WEEKS IT WILL TAKE TO COMPLETE THAT ITEM
ACTUAL DURATION=HOW MANY WEEKS IT TOOK TO COMPLETE THAT ITEM
ACTIVITY | ASSIGNED TO | PLAN START (RECOMMENDED) | PLAN DURATION | ACTUAL START | ACTUAL DURATION
PLAN PRE-PLANNING MEETING |  | 1
SET GOALS FOR EVENT (ENTERTAIN/INFORM) |  | 1
DETERMINE THE TYPE OF EVENT (CASUAL/FORMAL) |  | 1
DESIGNATE POINT OF CONTACT FOR EVENT (COORDINATOR) |  | 1
DETERMINE TIME/DATE |  | 1
ESTABLISH AN EVENT TIMELINE |  | 1
SCHEDULE A MOCK REHEARSAL OF RIBBON CUTTING |  | 1
PREDETERMINE LIST OF PHOTOS YOU WOULD LIKE TAKEN |  | 1
PREDETERMINE FLOW OF VIDEO IF YOU HAVE A VIDEOGRAPHER |  | 1
DELEGATE
EVENT SET UP (TABLES, FOOD, REFUSE) |  | 2
DESIGNATE A CONTACT FOR RSVP |  | 2
CHOSE EMCEE/SPEAKER |  | 2
DETERMINE GREETERS FOR EVENT (WHO IS GOING TO BE AT THE DOOR TO WELCOME) |  | 2
TOUR GUIDES (WHO IS GOING TO SHOW PEOPLE THE AROUND) |  | 2
CLEAN UP |  | 2
GUEST LIST
DETERMINE GUEST LIST |  | 3
FRIENDS/FAMILY
EMPLOYEES/BUSINESS PARTNERS
PROJECT PARTNERS (FINANCIERS/ARCHITECTS)
ELECTED OFFICIALS
NEIGHBORS (OTHER TENANTS)
OTHERS (LIST HERE)
DESIGN THE EVENT
DESIGN AN INVITATION |  | 4
CREATE THE INTERNAL AGENDA (SEE SAMPLE INTERNAL AGENDA) |  | 4
CREATE THE EXTERNAL AGENDA (SEE SAMPLE EXTERNAL AGENDA) |  | 4
ROOM LAYOUT |  | 4
DECIDE ON FOOD (WHO WILL PROVIDE THE FOOD) LIST THAT PARTY HERE |  | 4
PHOTOGRAPHER |  | 4
VIDEOGRAPHER |  | 4
FLORIST |  | 4
ENTERTAINMENT (MUSIC/PERFORMER) |  | 4
DETERMINE GUESTS OF HONOR (ARE YOU RECOGNIZING SPECIFIC PEOPLE IN ATTENDANCE) |  | 4
PURCHASE NECESSARY SUPPLIES |  | 6
PROCLAMATION FROM THE TOWNSHIP |  | 6
PROMOTE & POST
DISTRIBUTE HARD COPY INVITE TO GUESTS OF HONOR |  | 7
DISTRIBUTE GENERAL INVITE VIA SOCIAL MEDIA/EMAIL |  | 8
CREATE A PROMOTION TIMELINE (3 WEEKS, 2 WEEKS, 1 WEEK, DAY OF) |  | 9, 10, 11, 12
CONFIRM RSVP'S & GUESTS OF HONOR |  | 10
PRESS RELEASE (ANNOUNCEMENT) |  | 11
ENJOY
CONFIRM ALL VENDORS/TEAM ASSIGNMENTS FOR DAY OF (SEE SAMPLE INTERNAL AGENDA) |  | 10
MANAGE THE INTERNAL TIMELINE (COORDINATOR) |  | 12
REHEARSAL |  | 12
SEND THANK YOU'S (GUESTS OF HONOR, VOLUNTEERS, DONATIONS, VENDORS) |  | 12
PRESS RELEASE (RECAP OF THE EVENT) |  | 12
PRESS RELEASE RECOMMENDATIONS
West Side Leader
Akron Beacon Journal
Akron Life Magazine
The Loop
RIBBON CUTTING SUPPLIES RECOMMENDED
GIANT SCISSORS
LARGE RIBBON (MEASURE THE RIBBON CUTTING AREA & DOUBLE FOR STAGGED PHOTO SHOOTS)
LARGE BOWS (PRE MADE)
GROUND BREAKING SUPPLIES RECOMMENDED
CEREMONIAL SHOVELS
LARGE BOWS (PRE MADE)

## Budget
ESTIMATE
INVITATION
PROMOTION
AGENDA-PAPER
THANK YOU GIFT
PHOTOGRAPHER
VIDEOGRAPHER
FOOD/REFRESHMENTS
CULTERY/PAPER WEAR
MUSIC/ENTERTAINMENT
RIBBON CUTTING-LARGE SCISSORS, LARGE RIBBON

## Sample Internal Agenda
BLOCK | START | END | ACTIVITY | RESPONSBILE | OBJECTIVE (NETWORK/INFORM/ENTERTAIN) | SUGGESTED REMARK TOPICS
PRE |  |  | Prep AV for slideshow
PRE |  |  | Set Refreshments/Food
PRE |  |  | Agenda/Promo Pieces on Display
PRE |  |  | Proclamations in order
CONT |  |  | Refreshments/Slideshow
1 |  |  | Personel Engagment
2 |  |  | Gather speakers for Welcome
3 |  |  | Move audience attention to Welcome
4 |  |  | Welcome Remarks 1
5 |  |  | Welcome Remarks 2
6 |  |  | Welcome Remarks 3
7 |  |  | Prepare Proclamations for distribution
8 |  |  | Recognition-Contributions
13
14 |  |  | Transistion to Ribbon Cutting
15 |  |  | Prepare for Ribbon Cutting (Set Scissors; Pull Ribbon)
16 |  |  | Ribbon cutting ceremonial statement
17 |  |  | Ribbon Cutting/Photos
17 |  |  | Stagged Photos of Ribbon Cutting
18 |  |  | Personel Engagment Cont.
19 |  |  | Wrap

## Post Con
Opportunities
What can we do better?
Highlights
What did we do really well?
What did we gain from this event?
Did we meet new clients?
Did we discover a need in the community?